## 工作表1
模块名 | 子模块 | url | 方法 | 接口说明 | 完成情况 | 备注 | 完成情况颜色 | 含义
Identity | users | /v3/users | GET |  |  | 流程通，阿里缺少enable字段 |  | 完成
|  |  | POST |  |  | 可创建用户，但opestack api缺失一些字段，如手机号 |  | 流程通，字段不全
|  | /v3/users／{user_id} | GET |  |  | 阿里云不支持通过user_id索引用户信息，将username转换 成user_id |  | 流程不通，API对不上
|  |  | PATCH |  |  | 有些字段无法更新 |  | 阿里缺失API
|  |  | DELETE |  |  |  |  | 努力开发中
|  | /v3/users/{user_id}/password | POST |  |  | 阿里缺失修改密码api |  | 其他问题
|  | /v3/users/{user_id}/groups | GET
| Roles | /v3/roles | POST |  |  | 阿里创建角色必须绑定策略文档，（目前写死）
GET
|  | /v3/roles/{roles_id} | GET
|  |  | PATCH |  |  | 阿里仅能更新策略文档
|  |  | DELETE |  |  | 将rolename当作roleid可以删除
| Groups | /v3/groups | POST
GET
|  | /v3/groups/{group_id} | GET
PATCH
DELETE
|  | /v3/groups/{group_id}/users | GET
|  | /v3/groups/{group_id}/users/{user_id} | PUT
HEAD
DELETE
| Policy | /v3/policies | POST |  |  | openstack api创建policy没有提供policyname字段，阿里云创建时此字段必须。 阿里云其他接口也必须依赖policyname索引等。故认为无法实现
GET
|  | /v3/policies/{policy_id} | GET
PATCH
DELETE
Compute | Servers | /v2.1/{tenant_id}/servers | GET |  |  | 流程通，阿里缺少key_name等字段
|  |  | POST |  |  | 流程通，阿里缺少user_data等字段
|  | /v2.1/{tenant_id}/servers/detail | GET |  |  | 流程通，阿里缺少key_name等字段
|  | /v2.1/{tenant_id}/servers{server_id} | GET |  |  | 流程通，阿里缺少key_name等字段
|  |  | PUT |  |  | 流程通，阿里缺少accessIPv6等字段
DELETE
| Actions | /v2.1/{tenant_id}/servers/{server_id}/action | POST | addFixedIp |  | FixedIp映射到SwitchID
|  |  |  | addFloatingIp |  | FixedIp映射到PrivateIp
|  |  |  | attach |  | 流程通，volume某些属性不匹配
confirmResize
createImage
evacuate
|  |  |  | forceDelete |  | 映射到DeleteInstance
lock
pause
getConsoleOutput
os-getRDPConsole
os-getSerialConsole
os-getSPICEConsole
os-getVNCConsole
reboot
|  |  |  | rebuild |  | 无直接对应接口先调用删除接口再调用创建接口
|  |  |  | removeFixedIp |  | FixedIp映射到SwitchID
|  |  |  | removeFloatingIp |  | FixedIp映射到PrivateIp
rescue
resize
restore
resume
revertResize
shelve
shelveOffload
os-start
os-stop
unlock
unpause
unrescue
unshelve
addSecurityGroup
removeSecurityGroup
|  |  |  | createBackup(administrative) |  | openstack缺少对应的DiskId
injectNetworkInfo(administrative)
migrate(administrative)
os-migrateLive(administrative)
resetNetwork(administrative)
os-resetState(administrative)
| IPs | /v2.1/{tenant_id}/servers/{server_id}/ips | GET
|  | /v2.1/{tenant_id}​/servers/​{server_id}​/ips/​{network_label}​ | GET
| Flavors | /v2.1/​{tenant_id}​/flavors | GET |  |  | 流程通，阿里缺少OS-FLV-DISABLED:disabled，disk等字段
POST
|  | /v2.1/​{tenant_id}​/flavors/​{flavor_id}​ | GET
DELETE
|  | /v2.1/​{tenant_id}​/flavors/detail | GET |  |  | 流程通，阿里缺少OS-FLV-DISABLED:disabled，disk等字段
| Limits | /v2.1/​{tenant_id}​/limits | GET |  |  | 流程通，阿里缺少maxTotalKeypairs等字段
| Extensions | /v2.1/​{tenant_id}​/extensions | GET |  |  | 流程通，阿里缺少QuotaClasses，Hypervisors等字段
|  | /v2.1/​{tenant_id}​/extensions/​{alias}​ | GET |  |  | 流程通，阿里缺少QuotaClasses，Hypervisors等字段
Block Storage | Volumes | /v2/{tenant_id}/volumes | POST
GET
|  | /v2/{tenant_id}/volumes/detail | GET
|  | /v2/{tenant_id}/volumes/{volume_id} | GET
PUT
DELETE
|  | /v2/{tenant_id}/volumes/{volume_id}/metadata | GET
PUT
| Volumes action | /v2/{tenant_id}/volumes/{volume_id}/action
| Snapshots | /v2/{tenant_id}/snapshots | POST
GET
|  | /v2/{tenant_id}/snapshots／detail | GET
|  | /v2/{tenant_id}/snapshots／{snapshot_id} | GET
PUT
DELETE
|  | /v2/{tenant_id}/snapshots／{snapshot_id}/metadata | GET
PUT
Images | Images | /v2/images | GET
POST
|  | /v2/images/{image_id} | GET
PATCH
DELETE
DELETE
|  | /v2/images/{image_id}/actions/reactivate | POST
|  | /v2/images/{image_id}/actions/deactivate | POST
|  | /v2/images/{image_id}/file | PUT
GET
Networking | Networks | /v2/networks | GET
POST
POST
|  | /v2/networks/{network_id} | GET
PUT
DELETE
| Subnets | /v2.0/subnets | GET
POST
POST
|  | /v2.0/subnets/{subnet_id} | GET
PUT
DELETE
| Ports | /v2.0/ports | GET
POST
POST
|  | /v2.0/ports/{port_id} | GET
PUT
DELETE
| Lbaas | /v2.0/lbaas/loadbalancers | GET
POST
|  | /v2.0/lbaas/loadbalancers/{loadbalancer_id} | GET
PUT
DELETE
|  | /v2.0/lbaas/loadbalancers/{loadbalancer_id}/status | GET
|  | /v2.0/lbaas/listeners | GET
POST
|  | /v2.0/lbaas/listeners/{listener_id} | GET
PUT
DELETE
|  | /v2.0/lbaas/pools | GET
POST
|  | /v2.0/lbaas/pools/{pool_id} | GET
PUT
DELETE
|  | /v2.0/lbaas/pools/{pool_id}/members | GET
POST
|  | /v2.0/lbaas/pools/{pool_id}/members/{member_id} | GET
PUT
DELETE
|  | /v2.0/lbaas/health_monitors | POST
|  | /v2.0/lbaas/health_monitors | GET
PUT
DELETE
Object storage | Object storage | /v1/{account}/{container} | GET
PUT
DELETE
|  | /v1/{account}/{container}/{object} | PUT
COPY
DELETE